## Gantt Chart (hidden)
ZIPPER RAMP UP Draft
PROJECT TITLE |  | ZIPPER RAMP UP |  |  |  | DATE |  | [Date]
PROJECT MANAGER |  | [Project Manager's name]
STAKEHOLDERS
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE KW | 27 |  | 28 |  | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
0 | Development
0.1 | Design Freeze | Michi Kettner |  | TDB
0.2 | Packaing + Label | Danijel Juric
0.3 | SOP | Michi Kettner
0.4 | Certification | Michi Kettner
1 | Configuration Setup
1.1 | Product description | Michi Kettner |  | 27
1.2 | Prototype BOM | Michi Kettner |  | 27
1.3 | Parts Naming | Michi Kettner |  | 27
1.4 | Cost calculation | Philipp Winter |  | 28
2 | Supplier Setup
2.1 | Overview (Sourcing Strategy, Make or Buy, etc.) | Michi Kettner/Philipp Winter
2.2 | Supplier | Philipp Winter
| Purchasing/ INCOTERMS/ Customs | PW/ MG/ JS
2.2.1 | Supplier Reach out (RFQ & Sample Check) | Michelle Du/ Philipp Winter
2.2.2 | Risk analysis - critical parts & suppliers | Philipp Winter
2.2.3 | Supplier Forecast (Contracts + Reordering Points) | Philipp Winter
2.3 | Second source strategy: Critical Parts | Philipp Winter
3 | Production Setup
3.1 | Assembly stations | Michi Kettner
3.2 | Human resource planning | José Lemus
3.3 | Assembly Instructions | Michi Kettner
3.4 | Process Documentation | José Lemus
4 | Quality Processes Setup
4.1 | Inbound Quality Check Instructions | Michelle Du
4.1.1 | First Article Inspection | TBD
4.1.2 | AQL | TBD
4.2 | Production Quality Check | Michi kettner
4.2.1 | First Article Inspection | TBD
4.2.2 | AQL | TBD
5 | Logistics & Forecast Setup
5.1 | SAP Setup | Julia Schmahl
5.1.1 | Add Product | Julia Schmahl
5.1.2 | Add Suppliers | Julia Schmahl
5.1.3 | Add Parts | Julia Schmahl
5.1.4 | Add BOM | Julia Schmahl
5.2 | Shipping Process | Mario Grosek
5.2 | Define inventory structure | Mario Grosek
5.2.1 | Define packaging structure | Mario Grosek
5.2.2 | Define Serial Number process | Mario Grosek
5.2.3 | HS Code for non-EU shipping | Mario Grosek

## Insert Team Name Here
Timeline Template
PROJECT TITLE | [6 empty] | DATE
PROJECT TEAM | [6 empty] | WEEK
| TASK TITLE | TASK OWNER | DUE WEEK | Week Number | [13 empty] | STATUS | TOOL/ DOCUMENTATION | COMMENT | DEFINITION
|  |  |  | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
1 | Brainstorming
1.1 | *Insert Sub-tasks Here* | *Insert Initials Here*
1.2
1.2
1.3
1.4
2 | Product Development/Iteration
2.1
2.2
2.3
2.4
3
3.1
3.2
3.3